## Risk Register
Risk ID | Asset | Threat | Impact (H/M/L) | Likelihood (H/M/L) | Risk Score (Impact x Likelihood) | NIST CSF Function | Mitigation Steps | Owner | Status | Notes
R1 | Patient Records | Ransomware attack locks medical files | High | Medium |  | Protect, Recover | Daily backups, test restores, keep antivirus up to date | IT Security | Open
R2 | Staff Email | Staff might click a phishing email and lose their accounts | High | High |  | Protect, Detect | Enable MFA, train staff, block known bad domains | Security + HR | In Progress
R3 | Doctor Laptops | Doctor laptop gets lost or stolen with patient info | High | Medium |  | Protect, Respond | Turn on Bitlocker, add remote wipe, make laptops auto lock | IT Support | Open
R4 | Wi-Fi Network | Guest Wi-Fi not separated, attacker could jump to internal network | Medium | Medium |  | Protect, Detect | Separate guest and internal Wi-Fi, stronger passwords, WPA3 | Network Team | Planned
R5 | Billing System | Third-party billing vendor data breach | High | Medium |  | Identify, Protect | Vendor security checks, limit data shared, review contracts | Compliance | Open
R6 | Backups | Backups could fail or get infected | High | Low |  | Recover | Offline backups, test restores, separate accounts | IT Ops | In Progress
R7 | Medical Devices | Old equipment running outdated software | Medium | High |  | Protect | Patch when possible, segment network, restrict access | Clinical Eng | Open
R8 | User Accounts | Ex-employee account left active | Medium | Medium |  | Identify, Protect | Better offboarding process, quarterly account reviews | HR + IT | Open
R9 | Cloud Storage | Data in cloud storage made public by mistake | High | Low |  | Protect | Private by default, regular access checks, encrypt data | Cloud Admin | Planned
R10 | Incident Response | Slow reaction makes attacks worse | Medium | Medium |  | Respond | Write IR plan, assign roles, run tabletop drills | Security | In Progress